## Planning
Module Name | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status
Dashboard Design | 2021-09-20 | 2021-09-23

## Time Log
Date | Start Time | End Time | Hours (End Time - Start Time) | Module in Progress | Work Description
2021-09-17 | 9.00AM | 11.00AM | 2 | NA | Platform and tools setup
2021-09-17 | 1.00 PM | 3.00 PM | 2 | NA | Platform and tools setup
2021-09-17 | 5.00 PM | 9.00 PM | 4 | NA | Project understanding
2021-09-17 | 10.00 PM | 12.00 AM | 2 | NA | Project understanding
2021-09-18 | 9.00AM | 12.00 AM | 10 | NA | Project walkthrough, research and understanding
2021-09-19 | 8.00 AM | 11.00 AM | 3 | NA | Github and project environments setup
2021-09-19 | 1.00 PM | 3.00 PM | 2 | NA | Project research and understanding
2021-09-19 | 5.00 PM | 10.00 PM | 5 | Dashboard | Project understanding, Planning, started work, added app_settings, messages and common utils
2021-09-20 | 9.00 AM | 11.00 PM | 2 | Dashboard | Meetings and project understanding and planning and research
2021-09-20 | 1.00 PM | 3.00 PM | 2 | Dashboard | Meetings and project understanding and planning and research
2021-09-20 | 5.00 PM | 9.00 PM | 4 | Dashboard | Mock data API setup, Consuming mock data, Research
2021-09-21 | 9.00 PM | 11.00 PM | 2 | Dashboard-->AppBar | Planning and research
2021-09-21 | 5.00 PM | 9.00 PM | 4 | Dashboard-->AppBar | Completed Menu, Circular image, Notification in App bar (1st cut), consuming mock API
2021-09-21 | 11.00 PM | 12.00 AM | 1 | Dashboard | Planning and research
2021-09-22 | 1.00 PM | 3.00 PM | 2 | Dashboard | Introduction of new simplified data model
2021-09-22 | 4.00 pm | 5.00 PM | 1 | Dashboard | Rework on Dashboard structure
2021-09-22 | 6.00 PM | 9.00 PM | 3 | Dashboard | Actively searchning switch, Profile completed, jobs status UI pin up and their data connection with mock data
2021-09-22 | 11.00 PM | 12.00 AM | 1 | Dashboard | Started with Upcoming events and Job offers
2019-09-23 | 10.00 AM | 11.00 AM | 1 | Dashboard | Scrum + planning for Upcoming events and Job offers
2019-09-23 | 12.30 PM | 1.30 PM | 1 | Dashboard | Working on Upcoming events and Job offers data aware Carousel
2019-09-23 | 8.00 PM | 9.00 PM | 1 | Dashboard | Working on Upcoming events and Job offers data aware Carousel
2021-09-23 | 11.00 PM | 12.00 AM | 1 | Dashboard | Working on Upcoming events and Job offers data aware Carousel
2019-09-24 | 09.00 AM | 11.00 AM | 2 | Dashboard | Scrum + Upcoming events and Job Offers Carousel
2019-09-24 | 01.00 PM | 3.00 PM | 2 | Dashboard | Upcoming events and Job Offers Carousel completed
2019-09-24 | 5.00 PM | 9.00 PM | 4 | Dashboard | Working on Recent Searches
2021-09-24 | 11.00 PM | 12.00 AM | 1 | Dashboard | Recent Searches completed
2021-09-25 | 09.00 AM | 10.00 AM | 1 | Dashboard | Planning of Latest jobs and suggested jobs
2021-09-25 | 01.00 PM | 03.00 PM | 2 | Dashboard | Reworked on Dashboard to implement Provider mechanism for sharing of data
2021-09-27 | 9.00 AM | 11.00 AM | 2 | Dashboard | Scrum + Working on Latest Jobs
2021-09-27 | 01.00 PM | 6.00 PM | 5 | Dashboard | Completed functionality of Latest Jobs
2021-09-27 | 6.00 PM | 9.00 PM | 3 | Dashboard | Completed functionality of Suggested Jobs, Fixed Job Offers Carousel
2021-09-28 | 9.00 AM | 10.00 AM | 1 | Dashboard | Reworked on code for optimization
2021-09-28 | 5.00 PM | 9.00 PM | 4 | Dashboard | Meeting + Activity Searching component
2021-09-29 | 9.00 AM | 11.00 AM | 2 | Dashboard | Actively searching
2021-09-29 | 1.00 PM | 3.00 PM | 2 | Dashboard | Actively searching
2021-09-29 | 5.00 PM | 9.00 PM | 4 | Dashboard | Actively searching
2021-09-29 | 10.00 PM | 12.00 AM | 2 | Dashboard | Actively searching bug fix and completed
2021-09-30 | 8.00 AM | 11.00 AM | 3 | Dashboard | Upcoming events
2021-09-30 | 1.00 PM | 3.00 PM | 2 | Dashboard | Upcoming events
2021-09-30 | 8.00 PM | 10.00 PM | 2 | Dashboard | Upcoming events completed
2021-09-30 | 11.00 PM | 12.00 AM | 2 | Dashboard | Job Offers working
2021-10-01 | 9.00 AM | 11.00 AM | 2 | Dashboard | Job Offers completed